## Test Case Planning & Execution
TEST CASE PLANNING AND EXECUTION
TEST TITLE
COM617 DB Benchmark Test Plan
TEST DESCRIPTION
Unit tests to be created alongside the code and run via Github Actions
| TEST DESCRIPTION |  | TEST DEPENDENCIES | TEST CONDITIONS |  | TEST CONTROL
| Unit tests to be created alongside the code and run via Github Actions after each push to the repository. This test plan should make up a part of the CI/CD Pipeline and should be updated accordingly when features are added. The tests can also be run manually by the user using Pytest in the IDE. |  | The dependencies will vary as the software becomes more complex as some tests will require different databases to be run. | Tests are to be run automatically through Github actions. Tests should also be able to be run manually on branch using Pytest. |  | Test to be run automatically after each push by Github so should be in a controlled environment. To test manually, first close application then run through.
STEP ID | STEP DESCRIPTION | TEST DATE | EXPECTED RESULTS | ACTUAL RESULTS | PASS / FAIL | ADDITIONAL NOTES
1 | A test to check the Home Page opens | 2024-03-24 | Test Pass- The home page can be opened | Test Pass- The home page can be opened | PASS
2 | Downsampling Toggle can be selected for DB1 – (Clickhouse) | 2024-03-24 | Test Pass – The downsampling toggles can be selected for each database type | Test Pass – The downsampling toggles can be selected for each database type | PASS
3 | Increment the Downsample Number Input for each Database type – DB 1 (Clickhouse) | 2024-03-24 | Test Pass – The downsampling value is incremented by 1 to a value of 6 (min is 5) | Test Pass – The downsampling value is incremented by 1 to a value of 6 (min is 5) | PASS
4 | Set the Downsample Number Input for each Database type – DB 1 (Clickhouse) | 2024-03-24 | Test Pass – The downsampling value is set to a value of 5000 | Test Pass – The downsampling value is set to a value of 5000 | PASS
5 | Change the start date of each Database type – DB 1 (Clickhouse) | 2024-03-24 | Test Pass – The start date can be changed | Test Pass – The start date can be changed | PASS
6 | Change the end date of each Database type – DB 1 (Clickhouse) | 2024-03-24 | Test Pass – The end date can be changed | Test Pass – The end date can be changed | PASS
7 | Change the start time of each Database type – DB 1 (Clickhouse) | 2024-03-24 | Test Pass – The start time can be changed | Test Pass – The start time can be changed | PASS
8 | Change the end time of each Database type – DB 1 (Clickhouse) | 2024-03-24 | Test Pass – The end time can be changed | Test Pass – The end time can be changed | PASS
9 | Submit Button can be selected and data ingressed for each Database type – DB 1 (Clickhouse) | 2024-03-24 | Test Pass – The submit button can be selected and the data is imported | Test Expected Fail (Due to pytest timeout) - The submit button can be selected and the data is imported | PASS | Test times out after 3 seconds, set as XFAIL when it times out passes as it shows data is being imported
10 | Downsampling Toggle can be selected for DB 2 – (PostgreSQL)
11 | Increment the Downsample Number Input for each Database type – DB 2 (PostgreSQL)
12 | Set the Downsample Number Input for each Database type – DB 2 (PostgreSQL)
13 | Change the start date of each Database type – DB 2 (PostgreSQL)
14 | Change the end date of each Database type – DB 2 (PostgreSQL)
15 | Change the start time of each Database type – DB 2 (PostgreSQL)
16 | Change the end time of each Database type – DB 2 (PostgreSQL)
17 | Submit Button can be selected and data ingressed for each Database type – DB 2 (PostgreSQL)
18 | Downsampling Toggle can be selected for DB 3 – (TimescaleDB)
19 | Increment the Downsample Number Input for each Database type – DB 3 (TimescaleDB)
20 | Set the Downsample Number Input for each Database type – DB 3 (TimescaleDB)
21 | Change the start date of each Database type – DB 3 (TimescaleDB)
22 | Change the end date of each Database type – DB 3 (TimescaleDB)
23 | Change the start time of each Database type – DB 3 (TimescaleDB)
24 | Change the end time of each Database type – DB 3 (TimescaleDB)
25 | Submit Button can be selected and data ingressed for each Database type – DB 3 (TimescaleDB)
26 | All values can be edited and stay the selected values when the submit button is selected – DB 1 (Clickhouse)
27 | All values can be edited and stay the selected values when the submit button is selected – DB 2 (PostgreSQL)
28 | All values can be edited and stay the selected values when the submit button is selected – DB 1 (TimescaleDB)

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.